## Sheet1
ID | Task | Priority | Type | Release | Target Date | Responsible | Coded | Committed | Tested
1 | Scenario XSD | High | Design | R1 | 2012-07-31 | Gabriel
2 | Scenario DB schema | High | Design | R1 | 2012-07-31 | Alex
3 | DB schema for simulation settings | High | Design | R1 | 2012-07-31 | Alex
4 | DB schema for sensors | High | Design | R1 | 2012-07-31 | Alex
5 | XSD for simulation settings | High | Design | R1 | 2012-07-31 | Alex
6 | XSD for report request | High | Design | R1 | 2012-07-31 | Alex, Alexey
7 | Handling deletion of scenario elements - schema adjustment | High | Design | R1 | 2012-07-31 | Alex, Alexey
8 | Scenario import | High | Feature | R1 | 2012-08-07 | Elena
9 | Scenario export | High | Feature | R1 | 2012-08-07 | Elena
10 | Scenario update - add elements to, delete elements from an existing scenario, update scenario elements | Medium | Feature | R1 | 2012-08-31 | Elena
11 | Calibration | High | Feature | R1 |  | Gabriel
12 | Basic simulation | High | Feature | R1 |  | Gabriel
13 | Stochastic simulation | High | Feature | R1 |  | Gabriel
14 | Sensor implementation | High | Feature | R1 |  | Gabriel
15 | Particle filter | Medium | Application | R1 |  | Gabriel
16 | XML output satisfying sirius_output.xsd from simulation (‘simulate_output’ function) | High | Feature | R1 | 2012-07-01 | Elena | 2012-07-01 | 2012-07-01
17 | XML output satisfying sirius_output.xsd from DB (‘output’ function) | High | Feature | R1 |  | Alexey
18 | ‘list_*’ functions for scenarios, runs, aggregations | High | Feature | R1 |  | Alexey
19 | Calculation of basic performance measures (‘process’ function) | High | Feature | R1 |  | Alexey, Elena
20 | ‘*_data*’ functions exporting contents of data tables | High | Feature | R1 |  | Alexey
21 | ‘*_performance*’ functions exporting contents of performance tables | High | Feature | R1 |  | Alexey
22 | Aggregation of link data (‘process’ function) | High | Feature | R1 |  | Alexey
23 | Aggregation of signal data (‘process’ function) | Medium | Feature | R2 |  | Alexey
24 | Calculation of signal phase performance measures (‘process’ function) | Medium | Feature | R2 |  | Alex, Alexey
25 | Aggregation of signal performance measures (‘process’ function) | Medium | Feature | R2 |  | Alex, Alexey
26 | ‘clear_*’ functions | High | Feature | R1 |  | Elena
27 | Process report request and generate report in PDF, XLS, PPT | High | Feature | R1 |  | Alexey
28 | Event infrastructure implementation | High | Feature | R1 |  | Gabriel
29 | Events: change in lane number, fundamental diagram change, demand coefficient change | High | Feature | R1 |  | Gabriel
30 | Controller infrastructure implementation | High | Feature | R1 |  | Gabriel
31 | Controllers: ALINEA, HERO | High | Feature | R1 |  | Gabriel
32 | Pre-timed signal control | High | Feature | R1 |  | Gabriel
33 | Implementation of decision points and route segments | High | Feature | R1 |  | Gabriel
34 | DTA | Medium | Application | R2 |  | Gabriel
35 | Web service infrastructure for Sirius | Medium | Feature | R2 |  | Alex
36 | Simulation status and diagnostics schema | Medium | Feature | R2
37 | Set-valued predictor | Low | Feature | R2 |  | Alex
38 | Implementation of state-dependent fundamental diagrams – for trucks | Medium | Feature | R2
39 | ‘load’ function for 3rd party data such as PeMS | Medium | Feature | R2 |  | Elena
40 | Fix calibration to use data from Sirius DB | Medium | Feature | R2 |  | Gabriel
41 | Controllers: VSL +RM | Medium | Feature | R2
42 | Signal optimization | Low | Application | R2 |  | Gabriel
43 | Add imputation to calibration | Low | Feature | R2
44 | Computation of split ratios from OD input data | Low | Feature | R2
45 | Weaving revision | Low | Feature | R2 |  | Alex, Gabriel
46 | Complex controller that switches control plans based on the traffic state – design and implementation | Medium | Feature | R2 |  | Alex, Gabriel